## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-CV-DW-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0059 |  |  | Transmital Date: 22-Aug-2021
Document Title: Standard Drawing For Slope Protection Details |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0059 |  |  | Transmital Date: 22-Aug-2021
[5 empty] | CRS No: NISOC-CRS-K-GNRAL-PEDCO-000-CV-DW-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please provide a brief calculation for its sufficiency and stability of upper body. |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | پایداری شیب بر اساس مطالعات ژئوتکنیک و با شیب درج شده تامین می شود.
2 | to prevent water peneteration bellow the paving layer this distance do not seem to be sufficient |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
3 | cement type as per geotechnical report/recommendation min concrete strength for stair/paving as per project spec |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
4 | needs 1% slope |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
5 | Please show the reference of detail |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
6 | Mix design shall be rechecked with project standard |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
7 | Add concrete general notes, as reference |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
8 | Show ditches above and bellow the slope |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
9 | please display needed expansion and contraction joint details and requirements |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | نیازی نمی باشد.
10 | Does concrete poured monolithically? |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | بتن به بصورت مقطعی پس از اجرای هر ترانشه (در صورت استفاده از برم) اجرا می گردد.
11 | in other drawings you show different symbol |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اصلاح شد.
12 | Please show ditches top and bot of slope |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
13 | min width to be specified |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
14 | usage of handrail to be checked/specified. if so project reference detail drawing be presented including connection detail to the concrete |  | BK-SUR-ENG-CIV-00-01455 | 2021-09-04 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date:

## Sheet2
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001