## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-SP-0002-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0015 |  |  | Transmital Date: 28/JUL/2021
Document Title: Specification For Atmospheric Above Ground Welded Steel Tanks |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-0015 |  |  | Transmital Date: 28/JUL/2021
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازرس شخص ثالث می بایست توسط پیمانکار اصلی تعیین گردد، از این رو تعریف بر این اساس اصلاح گردد. |  | 00/2294/162504 | 1400/05/21 | نقطه نظرات کارفرمای محترم اعمال شد.
2 | بندی در ارتباط با Conflict Requirement به مدرک اضافه و مندرجات زیر این بخش نوشته شود"در صورت وجود تناقض در مندرجات این مدرک و یا وجود تناقض بین مندرجات این مدرک با دیگر مدارک پروژه و یا استانداردهای مرجع این موضوع می بایست به کارفرما منعکس گردد. تصمیم گیری در این شرایط با کارفرما خواهد بود. |  | 00/2294/162504 | 1400/05/21 | نقطه نظرات کارفرمای محترم در بند 3.5 اعمال شد.
3 | در مدرک درج شود هر جا به ویرایش استانداردی اشاره نشده است، منظور آخرین ویرایش موجود می باشد. |  | 00/2294/162504 | 1400/05/21 | نقطه نظرات کارفرمای محترم در بند 2 اعمال شد . لازم به ذکر است آخرین ویرایش استاندارد زمان عقد قرارداد ملاک عمل خواهد بود.
4 | کلمات Will,May,... دوبار (بندهای 1و4) در مدرک تعریف شده اند. |  | 00/2294/162504 | 1400/05/21 | نقطه نظرات کارفرمای محترم در بند 3.5 اعمال شد.
5 | این مدرک می بایست براساس آخرین ویرایش استانداردAPI 650 و با در نظر گرفتن کلیه الزامات استاندارد IPS-G-ME-100 بازنگری گردد. |  | 00/2294/162504 | 1400/05/21 | نقطه نظرات کارفرمای محترم در بند 5 اعمال شد.
6 | با توجه به اینکه استاندارد طراحی مخازن آب آشامیدنی Elevated Water Tank )با استانداردهای مرجع متفاوت است ضروریست این مبحث در مدرک جداگانه ارایه گردد. |  | 00/2294/162504 | 1400/05/21 | پیرو مذاکرات تلفنی با کارشناس محترم کارفرما، نقطه نظر ارایه شده، مرتفع شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 10/02/2021