## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0839 |  |  | Transmital Date: 4/18/2022
Document Title: Process Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0839 |  |  | Transmital Date: 4/18/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نام تجهیزات در عنوان و داخل مدرک و در هماهنگی با سایر مدارک پروژه یکسان درج گردد. |  | 1401-2294-68573 | 1401/02/31 | اعمال گردید.
2 | اصلاحات مربوط به مخزن H/C Close Drain , Slug Catcher , Flare K.O Drum و سایر تجهیزات متاثر از تصمیمات جلسه مورخ 01/02/28 در صورت تاییید گزینه مربوط به مهندسی ارزش در این مدرک و سایر مدارک لحاظ گردد. |  | 1401-2294-68573 | 1401/02/31 | اعمال گردید.
3 | نقطه نظرات این امور بروی مدرک Drum Sizing در این مدرک لحاظ گردد. |  | 1401-2294-68573 | 1401/02/31 | اعمال گردید.
4 | نقطه نظرات مطروحه بروی مدرک P&ID در خصوص نازل ها و اتصالات مخازن لحاظ گردد. |  | 1401-2294-68573 | 1401/02/31 | اعمال گردید.
5 | ابعاد برخی مخازن با ایعاد بدست آمده در مدرک Drum Sizing تفاوت دارد. |  | 1401-2294-68573 | 1401/02/31 | مورد بررسی قرار گرفته و اصلاحات در صورت نیاز اعمال گردیده است.
6 | با توجه به ابعاد مخزن V-2101 و وجود دمیستر بنظر میرسد نوع Top Head Flange مناسبتر باشد. |  | 1401-2294-68573 | 1401/02/31 | با توجه ابعاد مخزن و طبق Criteria نوع مخزن به درستی تعیین شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: