## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0839 |  |  | Transmital Date: 4/18/2022
Document Title: Process Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0839 |  |  | Transmital Date: 4/18/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نوع Demister pad نوشته شود. |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | مخازن با توجه به اطلاعات کمپرسور ساز و نیز استانداردهای طراحی سایز شده و در دیتاشیت فرآیندی قرار داده می شوند.نوع دمیسترپد در مکانیکال دیتاشیت ذکرمی گردد.
2 | نقطه نظرات ارائه شده در سايزينگ ظروف، در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | اصلاح گردید.
3 | كامنت پيشين: سايز نازل ها پس از نهايي سازي سايزينگ شير ايمني و شبكه فلر نهايي سازي مي گردد. |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | با توجه به سایزینگ شیرهای ایمنی، اصلاحات صورت گرفته است.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04217 | 2022-05-10 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: