## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0011 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0228 |  |  | Transmital Date:10/11/2021
Document Title: Process Data Sheets For Elevated Potable Water Tank |  |  |  |  | PEDCO Tr. No.BK-PEDCO-NISOC-0005-PR-TR-0228 |  |  | Transmital Date:10/11/2021
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-DT-0011 -D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم نهایی گردیدن مدارک سایزینگ مخازن به دلیل عدم ارسال محاسبات مصرف و یا سایر دلایل مطروحه طی پاسخ این امور بروی مدارک مربوطه طی نامه شماره 293081 این بخش از مدارک در این مقطع قابل صحه گذاری و بررسی نمی باشد |  | 1400-229-296922 | 1400/09/08 | مورد تاییید است.
2 | اطلاعات مربوط به متریال از این مدرک حذف گردد |  | 00/2290/296926 | 1400/09/08 | اعمال گردید.
3 | بخش Corrosive Comp تکمیل گردد |  | 00/2290/296926 | 1400/09/08 | H2S & Co2 در این بخش وارد شده اند.
4 | تعداد درین ها مطابق مدرک Design Criteria بازنگری گردد |  | 00/2290/296926 | 1400/09/08 | اعمال گردید.
5 | تغییرات مدرک P&ID از حیث تجهیزات کنترل و قطع اضطراری بروی این مدارک اعمال گردید |  | 00/2290/296926 | 1400/09/08 | اعمال گردید.
6 | حداقل تعداد Man Way مطابق P&ID مندرج در اسناد پیمان در نظر گرفته شود. |  | 00/2290/296926 | 1400/09/08 | حداقل تعداد Man Way با P&ID طراحی پایه مطابقت دارد.
7 | نام تجهیزات در برگ داده ها و سایر مدارک از قبیل P&ID به صورت یکسان درج گردد. |  | 00/2290/296926 | 1400/09/08 | مورد تاییید است.
8 | اطلاعات مندرج با مدارک P&ID ارسالی تفاوت قابل توجهی دارد که می بایست همسان سازی شود |  | 00/2290/296926 | 1400/09/08 | همسان سازی اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Aryafar | Signature
| Date: |  |  |  |  | Date: