## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0228 |  |  | Transmital Date: 10.Nov.2021
Document Title: Process Data Sheets For Fuel Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0228 |  |  | Transmital Date: 10.Nov.2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي سازي ايم مدرك منوط به نهايي شدن محاسبات ابعاد ظروف مي باشد. |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | مدرک مربوط به محاسبات ارسال گردید.
2 | متريال انتخابي در برگه داده فني مكانيك مورد بررسي قرار مي گيرد. |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | اعمال گردید.
3 | ارتفاع مخزن پس از ارسال محاسبات هيدروليك پمپ قابل بررسي مي باشد. |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | مدرک مربوط به محاسبات ارسال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-00-02156 | 2021-11-30 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: