## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-IN-DG-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0922 |  |  | Transmital Date: 9 May 2022
Document Title: Instrument Hook-up Diagram - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-922 |  |  | Transmital Date: 9 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد Reply Sheet نظر خاصی مطرح نمیباشد. |  | 1401-2294-78805 | 1401/03/08 | -
2 | جهت شستی shutdown کنار درب نفر رو محوطه چاه hook up لازم در نظر گرفته شود. |  | 1401-2294-78805 | 1401/03/08 | با توجه به محوطه کوچک فنس کشی شده و نزدیکی محل نصب تابلویWHCP به محل درب اضطراری ( کمتر از 5 متر) ، همچنین مطابق با مدارک WHCP HYDRAULICPNEUMATIC DIAGRAMS شاسی ESD برروی درب پانل طراحی شده و شاسی جداگانه در هیچیک از مدارک دیده نشده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 29 May 2022 |  |  |  |  | Date: