## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-IN-DG-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0922 |  |  | Transmital Date: 9 May 2022
Document Title: Instrument Hook-up Diagram - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-922 |  |  | Transmital Date: 9 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | براي متريال wetted part ، آخرين رويژن NACE در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | ملاحظه ودر نظر گرفته شده است.
2 | تفاوت بين آيتم هاي 01، 128 بررسي و در صورت وجود ذكر گردد. اين مورد در تمام آيتم ها جهت MTO بررسي گردد و قابل تعميم به موارد مشابه مي باشد. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | آیتم 128 مربوط به مسیر نمونه گیری شده از خطوط جریانی است و برای آن مراعات NACE لازم می ‌باشد ولی آیتم 1 مربوط به خط هیدرولیک و غیر NACE می باشد بنابراین این دو آیتم با وجود مشابهت از نظر NACE بودن ، متفاوت می باشد .
3 | با توجه به اينكه كانكشن مربوط به SSV و SSSV نهايي نيست،در صورت تغييرات سازنده تغييرات لحاظ گردد. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | مطابق باSPECIFICATION FOR WHCP/HPU (در قسمت 9.3) و هماهنگی مجدد با سازنده wellhead ، سایز کانکشن برای SSSV برابر با 1/4" , برای SSV برابر با 1/2" می باشد .
4 | طول Tube ها بر اساس آخرين مدارك پروژه نهايي خواهد شد. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | ملاحظه شد.
5 | Tag مربوط به WHCP ها ذكر گردد. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | اعمال گردید.
6 | بخش پايپينگ 1- بخش مراجع در مدرك اضافه شده و ليست استانداردهاي مرجع به خصوص IPS و مدارك پروژه بخصوص Piping Assembly (Hook-up) Drawing ذكر گردد. 2- بهتر است سايز شير مربوط به Piping قبل از اتصالات ابزاردقيق در نقشه ها ذكر گردد. |  | BK-SUR-ENG-INS-01-04475 | 2022-05-29 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 29 May 2022 |  |  |  |  | Date: