## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0010-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0517 |  |  | Transmital Date: 29-Jan-2022
Document Title: Calculation Note For LV Capacitor Bank of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-EL-TR-0517 |  |  | Transmital Date: 29-Jan-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صورت تغییر مدرک لیست بار ، این مدرک می بایست متناظر با تغییرات برای هر چاه اصلاح گردد. |  | 1400-2294-415826 | 1400-12-01 | با توجه به این موضوع که مدرک لیست بار در شماره نامه 54909 توسط آن کارفرمای محترم تایید شده است، در صورت هرگونه تغییر در لیست بارها مدرک فوق مجددا ویرایش خواهد شد.
2 | نسخه AFC مدارک صرفا در صورت رعایت کامل استاندارد شماره گذاری مناطق نفت خیز جنوب قابلیت انتشار در سازمان کارفرما را خواهد داشت. |  | 1400-2294-415826 | 1400-12-01 | شماره گذاری مدرک براساس توافقات انجام شده با آن کارفرمای محترم مطابق با MDL پروژه در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 12-Feb-2022 |  |  |  |  | Date: