## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-DW-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0684 |  |  | Transmital Date: 06-Mar-2022
Document Title: Installation Detail & Notes for Connection OHL to Gantries for Wells |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-EL-TR-0684 |  |  | Transmital Date: 06-Mar-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DW-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کلیه تجهیزات به کار رفته در نقشه دیاگرام تک خطی شامل دو مجموعه LA و یک مجموعه کات اوت فیوز و یک دستگاه LBS نمایش داده شوند |  | 1400-2294-451069 | 1400-12-24 | اعمال گردید.
2 | نقشه می بایست نماهای روبه رو و دید از بالا را نیز نمایش دهد. سکشن قسمتهای مختلف نیز نشان داده شود. |  | 1400-2294-451069 | 1400-12-24 | با توجه به اینکه امکان تامین تجهیزات به کار رفته در مدرک از وندورهای مختلف وجود داشته و نقشه های ابعادی و جزئیات آنها با هم تفاوت هایی دارد لذا مدارک تکمیلی درخواستی در VPISهای مربوطه وندور گنجانده و متعاقبا از ایشان اخذ و ارسال خواهد گردید.
3 | با توجه به عنوان نقشه می بایست جزییات کلیه اتصالات شامل کلمپها، فیتینگها و . . . نمایشداده شوند. |  | 1400-2294-451069 | 1400-12-24 | پیرو توضیحات بند فوق، جزئیات درخواستی از وندور اخذ و ارائه خواهد گردید.
4 | مطابق با استاندارد می بایست فاصله بین تجهیزات در نقشه مشخص گردد. (جدول فواصل استاندارد نیز در نقشه نمایش داده شود) |  | 1400-2294-451069 | 1400-12-24 | فواصل کلی و مهم در نقشه درج گردید.
5 | در بخش legend کلیه تجهیزات به کار رفته معرفی گردند. |  | 1400-2294-451069 | 1400-12-24 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 15-Mar-22 |  |  |  |  | Date: