## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0010-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0517 |  |  | Transmital Date: 29-Jan-2022
Document Title: Calculation Note For LV Capacitor Bank of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-EL-TR-0517 |  |  | Transmital Date: 29-Jan-2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-EL-CN-0010-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | This document shall be revised base on comments on load list. |  | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | با توجه به این موضوع که مدرک لیست بار در شماره نامه 54909 تایید شده است. لذا در صورت هرگونه تغییر در لیست بارها مدرک فوق ویرایش خواهد شد.
2 | According to our telephone conversation, the effect of transformer in capacitor bank sizing is not required and shall be deleted in calculation. |  | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | محاسبات مربوط به ترانس حذف گردید.
3 | Calculations shall be revised based on IRP Manufacturer data and recommendations. This document shall be revised after IRP Manufacturer data received. |  | BK-SUR-ENG-ELE-00-03024 | 2022-02-12 | در هنگام خرید پمپ های IRP و در صورت مغایرت مشخصات فنی سازنده با این مدرک، محاسبات مورد بازنگری قرار خواهد گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 12-Feb-2022 |  |  |  |  | Date: