## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-PEDCO-320-PL-DT-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0756 |  |  | Transmital Date:27-Mar-2022
Document Title: Data Sheets For Barred Tee |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0101-PL-TR-0756 |  |  | Transmital Date:27-Mar-2022
[5 empty] | CRS No:CRS-BK-PPL-PEDCO-320-PL-DT-0002-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش مراجع به Spec پروژه اشاره نشده است. |  | 01/2294/22785 | 1401/01/24 | در ویرایش D01 اشاره گردیده است.
2 | ضرورت درج اطلاعات فرایندی در مدرک مشخص نمی باشد. |  | 01/2294/22785 | 1401/01/24 | در جهت اطلاع سازنده به اطلاعات فرایندی اشاره گردیده است.
3 | از انجا که محاسبات ضخامت نهایی نشده است ، لذا انتخاب آن پس از انجام این محاسبات امکان پذیر خواهد بود. |  | 01/2294/22785 | 1401/01/24 | محاسبات ضخامت در مرحله فعلی نهایی گردیده است.
4 | با توجه به اینکه داده برگ فنی به منظور ساخت کالا کاربرد دارد ، لذا درج نقشه شماتیک کالا مطابق نقشه استاندارد در مدرک راهگشا خواهد بود. |  | 01/2294/22785 | 1401/01/24 | در ویرایش D01 اشاره گردیده است.
5 | با توجه به اینکه خطوط لوله X52 می باشند ، از این رو ضروریست متریال متناسب با جنس خط لوله انتخاب گردد. |  | 01/2294/22785 | 1401/01/24 | جنس خطوط لوله API 5L Gr. B می باشد.
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: