## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-CV-MT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0918 |  |  | Transmital Date:5/9/2022
Document Title: MTO For Civil Works - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-CV-TR-0918 |  |  | Transmital Date:5/9/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W028-PEDCO-110-CV-MT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | به اطلاع می رساند با عنایت به اینکه تاکنون نقشه های اجرایی این لوکیشن نهائی نشده اند، برای سازمان کارفرما مدارک فوق فقط جنبه ی اطلاع رسانی داشته و امکان بررسی جامع مقدور نمی باشد. |  | 1401-2294-59526 | 1401/02/22 | با توجه به اینکه نقشه های اجرایی چندین بار ورد بررسی و موشکافی کارفرمای محترم قرار گرفته است لذا ویرایش جدید با در نظرگرفتن تغییرات مدنظر ارائه می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: