## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0780 |  |  | Transmital Date: 06 APR 2022
Document Title:Block Diagram Configuration For Control/ESD/F&G System - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-IN-T-0780 |  |  | Transmital Date: 06 APR 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به كامنت شماره 6، تاييد ذي النفع اخذ گردد. |  | BK-SUR-ENG-INS-01-04007 | 2022-04-20 | سایز مانیتورها اصلاح و"32 گردید.
2 | با توجه به تغييرات احتمالي، موارد در اين مدرك نيز بروز رساني گردد. |  | BK-SUR-ENG-INS-01-04007 | 2022-04-20 | مدرک مطابق مدارک مرجع اصلاح و بروز رسانی گردید.
3 | باز گشت به كامنت شماره 4 مدرك قبلي و همچنين بازديد صورت گرفته مورد دقيقا بررسي و بيان گردد. |  | BK-SUR-ENG-INS-01-04007 | 2022-04-20 | مطابق كامنت شماره 4 مدرك قبلي، Note4 از مدرک حذف گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 Apr 2022 |  |  |  |  | Date: