## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DT-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0660 |  |  | Transmital Date: 2 Mar 2022
Document Title: Data Sheets For Temperature Gauge - Wellheads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-IN-TR-0660 |  |  | Transmital Date: 2 Mar 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | بازگشت به كامنت شماره 1، دليل قانع كننده اي براي نصب ابزاردقيق در زاويه 45 درجه ارائه نشده است. بر اساس نقشه استاندارد مرجع در نقشه P&ID زاويه 45 درجه ذكر نشده است. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید و TG بطور مستقیم نصب می شود.
2 | موارد مربوط به PURCHASE به Will be finalized later تغيير پيدا كند. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید
3 | بين مدرك ديتاشيت و creiteria و spec در مورد accuracy تناقض وجود دارد. مدارك بايد با هم هم خواني داشته باشد. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | دقت در این مدرک صحیح می باشد و در مدارک دیگر در صورت مغایرت اصلاح می گردد.
4 | متريال pointer درج گردد. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید
5 | Flange Connection در نظر گرفته شود. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید
6 | شماره استاندارد براي محاسبه u lentgh درج گردد. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید
Process Comments
7 | بنظر مي رسد عبارت" Measuring Range (bar)" براي اين تجهيز نياز به بازنگري دارد. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | مطابق با مدرک SPECIFICATION FOR INSTRUMENTATION در قسمت 12.2.5 این measuring range اصلاح گردید.
8 | عبارت MIX در قسمت Fluid مي بايست به HC +Water تغيير يابد. |  | BK-SUR-ENG-INS-00-03646 | 2022-03-14 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Mar 2022 |  |  |  |  | Date: