## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0828 |  |  | Transmital Date: 17 Apr 2022
Document Title: Instrument Earthing Typical Diagram |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0828 |  |  | Transmital Date: 17 Apr 2022
[5 empty] | CRS No: CRS-PEDCO-BK-GCS-PEDCO-120-IN-DG-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به ماهيت مدرك IFI مسئوليت تمامي موارد بر عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | مورد ملاحظه قرار خواهد گرفت.
2 | در صورت تغييرات در مدارك پيش نياز مانند spec و ... در اين مدرك نيز منعكس شود. |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | هرگونه تغییری در مدارک فوق در این مدرک و مدارک مرتبط اعمال می گردد.
3 | تعداد دقيق چاههاي زمين با توجه به نيازمنديهاي پروزه بصورت دقيق مشخص گردد |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | محاسبه تعداد چاه یا تعداد میله Rod مورد نیاز پروژه در مدرک Calculation Note For Earthing & Lightning آمده است که بر همین اسا س مدرک Overall Earthing Layout تولید گردیده است. مدارک مربوطه به عنوان مرجع در مدرک اشاره گردید.
4 | توصيه ميشود تقسيم بندي Junction Box ها بر اساس كابل ها صورت بگيرد: Typical Junction Box (for Multi cables with Overall Screen) Typical Junction Box (for Multi cables with Overall & Individual Screen) |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | نظرات کارفرمای محترم در مدرک اعمال گردید.
5 | ليست مدارك مرجع پروژه مشخص شود. |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | نظرات کارفرمای محترم در مدرک اعمال گردید.
6 | با توجه به نوت شماره 15، اين نكته توجه شود كه وندورهاي سيستم ها و ... بايد از مدارك پيوست پروژه تبعيت كنند. در غير اين صورت تاييد كارفرما براي هر گونه تغيير اخذ گردد. |  | BK-SUR-ENG-INS-01-04154 | 2022-05-07 | مورد ملاحظه قرار خواهد گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 7 May 2022 |  |  |  |  | Date: