## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0002-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0473 |  |  | Transmital Date: 18-Jan-2022
Document Title: MECHANICAL DATA SHEETS FOR 1st STAGE G.C. SUCTION DRUMS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-0473 |  |  | Transmital Date: 18-Jan-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرآیندی براساس آخرین ویرایش مدارک در مدرک گنجانده شود. |  | 00/2294/386730 | 1400/11/09 | با توجه به آخرین اطلاعات و طبق مدرک Process Data Sheet اصلاح گشته است
2 | فشار عملیاتی مطابق با اسناد پیمان در نظر گرفته شود. |  | 00/2294/386730 | 1400/11/09 | بر اساس محاسبات صورت گرفته و فایل شبیه سازی ایستگاه فشار عملیاتی مشخص گردیده اشت.
3 | دلایل تغییر ابعاد مخزن نسبت به اسناد پایه بیان گردد. خاطر نشان می شود ادعای تغییر کار در این خصوص پذیرفتنی نیست. |  | 00/2294/386730 | 1400/11/09 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است.
4 | الزام سازنده به ارائه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 00/2294/386730 | 1400/11/09 | در یادداشت 41 اشاره شده است.
5 | تعیین میزان C.A پس از انجام مطالعات خوردگی امکان پذیر خواهد بود. |  | 00/2294/386730 | 1400/11/09 | مطالعات خوردگی ارسال شده است. میزان C.A بر این اساس در دیتاشیت وارد شده است.
6 | با توجه به اینکه تغییرات مندرج در مدرک در ویرایش قبل بیان نشده است ضرروی است دلایل بروز این تغییرات بیان گردد. لازم به ذکر است موارد این چنینی در دیگر مدارک نیز تکرار شده است که پذیرفتنی نبوده و می بایست این روال اصلاح گردد. |  | 00/2294/386730 | 1400/11/09 | نظر کارفرمای محترم مد نظر قرار می گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature H.Naserizadeh |  |  |  | Clarified By: H.Adineh | Signature
| Date: 22/01/2022 |  |  |  |  | Date: 27/07/2022