## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0002-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0473 |  |  | Transmital Date: 18-Jan-2022
Document Title: MECHANICAL DATA SHEETS FOR 1st STAGE G.C. SUCTION DRUMS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-0473 |  |  | Transmital Date: 18-Jan-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | FV/9 |  | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | اعمال گردید
2 | بر اساس استاندارد ASTM به صورت کامل نوشته شود. SA 283 Gr.C/ SA 516 Gr.60N / SA 106 Gr.B / SA 105 N |  | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | بر اساس ASTM نام گذاری به صورت A 105 است که معادل SA 105 در استاندارد ASME II می باشد.
3 | جانمایی نازل ها در نمای Top View با نمای سمت چپ تناقض دارد. اصلاح گردد. |  | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | نمای سمت چپ، نمای Elevation view است و تنها ارتفاع نازل ها در آن باید چک شود. این نما نمیتواند با نمای از بالا که در آن زوایای قرارگیری نازل ها مهم است در تناقض باشد.
4 | B1, 8" |  | BK-SUR-ENG-MEC-00-03607 | 2022-03-15 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature H.Naserizadeh |  |  |  | Clarified By: H.Adineh | Signature
| Date: 22/01/2022 |  |  |  |  | Date: 27/07/2022