## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W018S-PEDCO-110-IN-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0334 | Transmital Date: 13 Dec 2021
Document Title: PMR For Field Instrumentations - W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0009-IN-TR-0334 | Transmital Date: 13 Dec 2021
[5 empty] | CRS No:CRS No: NISCO-CRS-BK-W018S-PEDCO-110-IN-MR-0002_D00 | CRS Status:
Item |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) | Client Conclusion
1 | مطابق رویه تولید مدارک فنی ، زبان انگلیسی جهت تولید این اسناد ذکر شده است استفاده از چند زبان در مدرک چه در سربرگ چه در متن مورد قبول نمی باشد. |  | 1400-2294-330276 | 1400/10/01 | سربرگ فارسی مطابق با MDL پروژه می‌باشد
2 | مطابق مدرک MDL شماره چاه در کنار عنوان اصلی مدرک ذکر گردد. |  | 1400-2294-330276 | 1400/10/01 | اعمال گردید.
3 | با توجه به نهایی نشدن مدارک دیتا شیت ، اصلاحیه این مدرک پس از نهایی شدن دیتاشیت ها ارسال گردد. |  | 1400-2294-330276 | 1400/10/01 | ملاحظه گردید
4 | قسمت قطعات مدرک مطابق بخش قطعات یدکی مدرک Specification For Inetrumentation همسان سازی گردد. |  | 1400-2294-330276 | 1400/10/01 | اعمال گردید (قسمت 5.2 اصلاح گردید).
5 | برای تمام مدارک فوق بخش 4.0 در جدول قسمت Remarks مدرک SPECIFIC ATION FOR INSTRUMENT ATION نیز ذکر گردد. |  | 1400-2294-330276 | 1400/10/01 | اعمال گردید.
6 | در بخش 12 پیوشت 1 ، مدارک و مراجع ابزار دقیق ، مدرک INSTRUMENT & CONTROL SYSTEM BASIS OF DESIGN ذکر گردد. |  | 1400-2294-330276 | 1400/10/01 | اعمال گردید.