## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-IN-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0334 |  |  | Transmital Date: 13 Dec 2021
Document Title: PMR For Field Instrumentations - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0009-IN-TR-0334 |  |  | Transmital Date: 13 Dec 2021
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comment
1 | Please clarify the reason of considering the Purpose of Issue/Status of MR in IFI format? |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | it is considered according to MDL .
2 | Regarding to reference documents like datasheets and specification are commented (Major Comments), this document cannot be reviewed. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | all of reference documents have been revised & updated according to last comments
3 | Document Number for Data Sheet For temperature gauge - Wellheads to be added in page 6. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
4 | Regardding to wellhead's P&IDs are commented, the responsibility of any changes in Tag numbers (Time and cost impact) are in contractor's scope of work. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
5 | Instrument & Control System Design Criteria document shall be added as reference document. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
6 | Minimum requirement of FAT/SAT to be specified. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | Min requirement for FAT and SAT are mentioned in reference document, "Specification For Instrumentation BK-GNRAL-PEDCO-000-IN-SP-0001"
7 | Instruction To Bidders (ITB) section (including: Bidding stage, Vendor Proposal Presentation, Ordering Stage, Delivery, Training , …) shall be provided as a section. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | Common Format for all PMRs are used . Please Refer to reference documents.
8 | ITP (Inspection Test Plan) Table to be be provided. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | ITP table will be provided by vendor which shall be approved by client.
9 | Document Number for PROJECT SPARE PART SUPPLY PROCEDURE (Doc. No. E&D-QC-SP-1) in section 5.2 to be re-checked. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
QA/QC Comments
9 | در بند 5.1.1، عبارت QA Organization به QA/QC Organization Chart تغيير يابد. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
10 | در بند 6: 1-عبارت "Project ITP Procedure" به "Commodity Procurement and Manufacturing Inspection Instruction" تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. 3- شماره مدرك E&D-QC-INSP-1 حذف گردد. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1,2 . items 1,2 have been noted. 3. item 3 shall not be removed , document number of item 3 has been changed to E&C-QC-SP-1 .
11 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل بازرسي كالا و تجهيزات به شماره E&D-QC-INSP-1 حذف گردد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV01 اضافه گردد. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1. the document of item 1 has been changed to E&C-QC-INSP-1 2. noted.
12 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachment 2" حذف گردد. 2. مدارك مشخص شده در سر فصل هاي Quality, Manufacturing, Testing تجميع شده و در يك سر فصل تحت عنوان مدارك QA/QC آورده شود. 3- عبارت "List of Documents will be Finalized in VDLS" به عنوان نوت اضافه گردد 4. Final Data Book اضافه شود. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | 1. noted 2.noted 3.noted 4. noted
13 | ساير نقطه نظرات روي مدرك درج گرديده است. |  | BK-SUR-ENG-INS-00-02455 | 2021-12-27 | noted.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari M.Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Dec 2021 |  |  |  |  | Date: