## Sheet1
براي
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0004_D00 | [5 empty] | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0509 |  |  | Transmital Date: 25 Jan 2022
Document Title:Instrument/F&G Cable Trench/Route Layout Drawing | [5 empty] | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-IN-TR-0509 |  |  | Transmital Date: 25 Jan 2022
[6 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مواردي مانند BD-103، BD-104 و ... مشخص شود. |  |  | "BK-SUR-ENG-INS-00-03017 | 2022-02-09 | درخواست کارفرمای محترم اعمال گردید
2 | ارتباط بين اتاق كنترل قديم و جديد بررسي شود. |  |  | "BK-SUR-ENG-INS-00-03017 | 2022-02-09 | درخواست کارفرمای محترم انجام شد. برای این ارتباط از مسیر موجود بین اتاق کنترل موجود و اتاق برق موجود و مسیر جدید از اتاق برق موجود به اتاق کنترل جدید استفاده میشود
3 | براي جلوگيري از ابهام، تجهيزات موجود، بصورت Existedمشخص شود. |  |  | "BK-SUR-ENG-INS-00-03017 | 2022-02-09 | تجهیزات موجود به صورت خاکستری در مدرک نمایش داده شده اند.
4 | مطابق قرارداد، تمام مسيرها بايد بصورت زير زميني باشد. |  |  | "BK-SUR-ENG-INS-00-03017 | 2022-02-09 | مسیرها به صورت زیر زمینی- دفنی در نظر گرفته شده است.
5 | با توجه به اينكه، مدارك پيش نياز مانند plot plan و ... مربوط به اين مدرك نهايي نشده است در صورت تغيير در هر كدام از موارد مدرك بروز رساني گردد. |  |  | "BK-SUR-ENG-INS-00-03017 | 2022-02-09 | مدرک مطابق آخرین تغییرات به روز رسانی کردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  |  | Clarified By: | Signature
| Date: 8 Feb 2022 | [5 empty] | Date: