## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0028-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0815 |  |  | Transmital Date: 16/Apr/2022
Document Title: Mechanical Data Sheets For Fire Water Jockey Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-ME-TR-0815 |  |  | Transmital Date: 16/Apr/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0028-D01 |  |  | CRS Status:
item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است پمپ های جوکی تابلوی کنترل جداگانه داشته باشند. |  | 01/2294/55015 | 1401/02/19 | به اطلاع کارفرمای محترم میرساند برای پکیج آب آتش نشانی تابلوی کنترلی مجزا برای موتورهای جوکی و موتور اصلی در نظر گرفته شده است که در مدارک MR و مکانیکال دیتاشیت مربوطه ذکر می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 5/7/2022 |  |  |  |  | Date: 07/30/2022