## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PI-RT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0550 |  |  | Transmital Date: 2/5/2022
Document Title: CORROSION STUDY & MATERIAL SELECTION REPORT |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-PI-TR-0550 |  |  | Transmital Date: 2/5/2022
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PI-RT-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | - در خصوص حد مجاز خوردگی خط لوله 8 اینچ گاز نقطه نظر دیگری مطرح نمی باشد. |  | 00/2294/443249 | 1400/12/19 | --
2 | - در خصوص خط لوله 4 اینچ مایعات گازی پیش بینی نرخ خوردگی بر اساس نرم افزار Predict ارائه نشده است. ضمنا همانگونه که در ویرایش قبلی و جلسه مورخ 1400/10/15 اعلام گردید به منظور بررسی موضوع و مشخص نمودن تزریق مواد کند کننده خوردگی در بالادست، نیاز به نقشه های P&ID می باشد. لذا لازم است علاوه بر نتایج نرم افزار Predict ، مدارک مرتبط از جمله P&ID و PFD همرا با ویرایش بعدی در اختیار این امور قرار گیرد. |  | 00/2294/443249 | 1400/12/19 | - با توجه به حذف خط لوله 4 اینچ از شرح کار پروژه (طی مطالعات مهندسی ارزش تایید شده)، این مدرک با وضعیت Approved ارائه می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: