## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-TB-0001-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-1039 |  |  | Transmittal Date: 06/Jun/2022
Document Title: TBE for Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-1039 |  |  | Transmital Date:06/Jun/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-ME-TB-0001-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical comments
1 | مدارک ارسالی در برگیرنده پیشنهادات فنی سازندگان که از سوی مشاور مهندسی پروژه Commented شده است و موارد و ابهامات از سوی سازندگان شفاف سازی نشده است، لذا ارایه آن در قالب TBE اقدام زودهنگام و شتابزده تلقی می گردد. |  | 01/2294/111535 | 1401/03/31 | نقطه نظر کارفرمای محترم مد نظر می باشد.
2 | معرفی کامل سازندگان به همراه ارایه سوابق کاری و تجربیات پیشین الزامی است. |  | 01/2294/111535 | 1401/03/31 | نقطه نظر کارفرمای محترم مد نظر می باشد.
3 | مطابقت کامل موارد فنی درج شده در جدول TBE با مندرجات داده برگها ضروری است. |  | 01/2294/111535 | 1401/03/31 | نقطه نظر کارفرمای محترم مد نظر می باشد.
4 | جداول مربوط به TBE تکمیل نشده است. |  | 01/2294/111535 | 1401/03/31 | جدول تکمیل شد.
5 | فرم رفع مغایرت فنی TCL تکمیل نشده است. |  | 01/2294/111535 | 1401/03/31 | فرم های مذکور تکمیل شدند.
6 | مندرج در پیشنهاد فنی پذیرفتنی نیستو تاکید می گردد دستورالعمل بازرسی میبایست در جلسه PIM و با حضور کارفرما، پیمانکار، بازرس شخص ثالث و سازنده نهایی گردد. لازم به ذکراست برگزاری جلسه مذکور منوط به بررسی مدارک بازرس شخص ثالث و تایید آن خواهد بود. |  | 01/2294/111535 | 1401/03/31 | نقطه نظر کارفرمای محترم مد نظر می باشد.
7 | کلیه کالاهای مورد نیاز ساخت میبایست توسط سازنده /تامین کنندگان مجاز تهیه گردد. لازم به ذکر است ارایه لیست سازنده / تامین کنندگان ضروری است. |  | 01/2294/111535 | 1401/03/31 | نقطه نظر کارفرمای محترم مد نظر می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M.ESMAEILI | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 4/25/2022 |  |  |  |  | Date: