## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0910 |  |  | Transmital Date: 8-May-2022
Document Title: Rough Grading Plans -W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0910 |  |  | Transmital Date: 8-May-2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-CV-DW-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 289630 مورخ 1400/11/11 اشاره گردید، به دلیل اینکه تاکنون نقشه های مدیریت پسماند چاه مورد اشاره توسط بخش تحت الارضی کارفرما تائید نشده است بنابراین در این مرحله این بخش از نقشه قابل بررسی نبوده که پس از تعیین تکلیف نهایی، اعلام نظر خواهد شد. |  | 01-2294-59411 | 1401/02/21 | طرح مدیریت پسماند طی نامه شماره 1401/2295/84838 مورخ 1401/03/10 تائید گردید و بر این اساس نقشه مورد بازنگری قرار گرفته و جهت بررسی تقدیم می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: