## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0936 |  |  | Transmital Date: 11 May 2022
Document Title: Typical Instrument Installation Drawing - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-0936 |  |  | Transmital Date: 11 May 2022
[5 empty] | CRS No: NISCO-CRS-BK-W007S-PEDCO-110-IN-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در قسمت نصب junction box ها، سایبان نیز در نظر گرفته شود |  | 1401-2294-102599 | 1401/03/24 | محل نصب این JB ها یا زیر shelter می باشد یا این jb ها برای شرایط سایت برای موقعیت های افتابی و بارانی طراحی گردیده است که در هر دو صورت نیاز به سایبان ندارد در ضمن این jb ها دارای IP65 می باشد .
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 May 2022 |  |  |  |  | Date: