## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-CV-RT-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1113 |  |  | Transmital Date: 25-Jun-2022
Document Title: Site Visit Report (Civil Work) - BK12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1113 |  |  | Transmital Date: 25-Jun-2022
[5 empty] | CRS No: NISOC-CRS-BK-BK12-PEDCO-110-CV-RT-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اجرای تمام عملیات ساختمانی در چارچوب شرح قرارداد مدنظر این امور می باشد |  | 01/2294/130256 | 1401/04/14 | مطابق با شرح قرارداد عمل خواهد شد.
2 | اعلام هرگونه انحراف نسبت به اسناد و مدارک پیمان در این گام به هیچ عنوان موضوعیتی ندارد. پیشتر در مرحله Endorsement تمامی مدارک دیسیپلین سیویل توسط شرکت پتروایران پذیرفته و تایید شده است. |  | 01/2294/130256 | 1401/04/14
3 | دیدگاه کارفرما، اجرای تمامی تعهدات پیمان مطابق با برنامه زمانبندی مصوب است. هرگونه تاخیر در این امر تاثیر مستقیم در پیامدهای پس از رخدادهای طبیعی پیش بینی نشده دارد. لذا پیشنهاد هرگونه اصلاح در عملیات ساختمانی در تعهد آن پیمانکار بوده و هیچ ادعایی پذیرفته نخواهد شد. |  | 01/2294/130256 | 1401/04/14
| A- BK-12 |  | 01/2294/130256 | 1401/04/14
| دیدگاه ها مطابق ذیل و متناظر با جدول صفحه 25 این گزارش اعلام می گردد. |  | 01/2294/130256 | 1401/04/14 | مطابق با شرح قرارداد عمل خواهد شد.
| ردیف 5 - مسیر برق رسانی-صفحه 23 - به اطلاع می رسد، نقشه های پلان پروفایل اشاره شده در گزارش مربوط به خطوط انتقال برق، پس از بررسی و اظهارنظر اداره مهندسی نقشه برداری اطلاع رسانی خواهد شد. |  | 01/2294/130256 | 1401/04/14 | ردیف اشاره شده با توجه به نامه اخیر کارفرمای محترم (شماره 01/2294/156807 تاریخ 1401/05/05) مبنی بر تغییر مسیر برقرسانی به دلیل رعایت حریم چاه 12 اصلاح شد. جزئیات در مدرک اشاره شده ارائه خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: