## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-DT-0001-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0861 |  |  | Transmital Date: 25-Apr-2022
Document Title: Data Sheets For UPS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-EL-TR-0861 |  |  | Transmital Date: 25-Apr-2022
[5 empty] | CRS No: NISOC-BK-GCS-PEDCO-120-EL-DT-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
3 | لازم است در مدرک، به دوره آموزشی تخصصی تعمیرات و عیب یابی دستگاه برای حداقل 5 نفر، توسط شرکت سازنده اشاره گردد. |  | 1401-2294-91107 | 1401-03-17 | مطابق با شرح کار پروژه، آموزش در دستور کار این پیمانکار می باشد که متعاقبا لحاظ خواهد شد. لذا خواهشمند است از ذکر این موضوع در داده برگه صرف نظر گردد و در آینده مطابق با شرح کار در نظر گرفته شود..
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 09-May-22 |  |  |  |  | Date: