## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-BD-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0801 |  |  | Transmital Date:10 Apr 2022
Document Title: Block Diagram Configuration For Control/ESD/F&G System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-0801 |  |  | Transmital Date:10 Apr 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-BD-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك مربوط به اين مدرك هنوز نهايي نشده است، لذا در صورت تغيير در هركدام از مدارك مربوطه، لازم است اين مدرك نيز بروز رساني شود. |  | BK-SUR-ENG-INS-01-04119 | 2022-05-01 | مدرک مطابق آخرین توافقات صورت گرفته در جلسه HAZOP اصلاح و بروز رسانی گردید.
2 | در اين برهه و با توجه به مفاد ماده 13 شرايط عمومي پيمان، نظر خاصي مطرح نمي باشد. |  | BK-SUR-ENG-INS-01-04119 | 2022-05-01 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 May 2022 |  |  |  |  | Date: