## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0015 |  |  | Transmital Date: 28/JUL/2021
Document Title: Standard Detail Drawing For Pressure Vessels and Heat Exchangers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-0015 |  |  | Transmital Date: 28/JUL/2021
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DW-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در ابتدای مدرک لیست نقشه ها با عناوین شماره نقشه، عنوان نقشه و شماره استاندارد مرجع اضافه گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
2 | بند 1: بازرس شخص ثالث می بایست توسط پیمانکار اصلی تعیین گردد، از این رو تعریف بر این اساس اصلاح گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
3 | در مدرک درج شود هرجا به ویرایش استانداردی اشاره نشده است، منظور آخرین ویرایش موجود می باشد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
4 | ضروریست شماره نقشه استاندارد مرجع در هر نقشه درج گردد و چنانچه نقشه های ارائه شده تفاوتی با نقشه استاندارد مرجع داشته باشند با ابرک نشان داده شوند. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
5 | نقشه های ارائه شده در این مدرک با اساس نقشه های استاندارد مناطق نفتخیز جنوب که به آن اشاره شده است مغایرت دارد به عنوان مثال ابعاد و اطلاعات مندرج در تمام صفحات مشخصات تجهیزات (Name Plate)، با نقشه های استاندارد تناقض دارد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
6 | توضیحات مربوطه به بند 6 مدرک شماره ME-DW-0002 در تهیه این مدرک نیز رعایت گردد. |  | 00/2294/162504 | 1400/05/21 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 8/8/2021 |  |  |  |  | Date: 8/01/2022