## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PL-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0592 |  |  | Transmital Date:1400/11/23
Document Title: PIPELINE STANDARD DRAWING FOR LINE MARKER POST AND CATHODIC PROTECTION SYSTEM |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-CV-TR-0592 |  |  | Transmital Date:1400/11/23
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-CV-DW-0037_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | واحد مقاومت فشاری بر حسب واحد متریک در مدرک درج گردد. |  | 00/2294/318687 | 1400/09/23 | اعمال گردید.
| در NOTE تیپ سیمان بر اساس نتایج گزارش ژئوتکنیک مشخص شود. |  | 00/2294/318687 | 1400/09/23 | اعمال گردید.
| جزئیات نصب سیستم حفاظت کاتدی که قبلا با ترنسمیتال TR-0116 جهت این اور ارسال شده بود طی نامه شماره 232456 مورخ 1400/07/21 مورد تائید قرار گرفته لذا ادغام مدارک سیستم حفاظت کاتدی و مدارک دیگر موضوعیت ندارد. |  | 00/2294/318687 | 1400/09/23 | بنابر نظر کارفرمای محترم جزئیات مربوط به حفاظت کاتدیک از این نقشه حذف و نقشه اصلاح گردید.
| با توجه به MDR تائید شده پروژه بعنوان مدرک به PIPELINE STANDARD DRAWING FOR LINE MARKER اصلاح شده و موارد مرتبط با حفاظت کاتدیک از مدرک حذف گردد. |  | 00/2294/318687 | 1400/09/23 | اصلاح شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: