## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PL-DW-0001-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0303 |  |  | Transmital Date: 07-Dec-2021
Document Title: Pipeline Standard Drawing For Line Marker |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-0303 |  |  | Transmital Date: 07-Dec-2021
[5 empty] | CRS No: CRS-BK-GNRAL-PEDCO-000-PL-DW-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه جزييات مربوط به حفاظت كاتدي در مدرك شماره BK-GNRAL-PEDCO-000-EL-DW-0005_D01 ارائه شده و اين مدرك توسط پتروايران و مناطق نفت خيز تاييد شده است لذا نيازي به ارائه اين مدارك در بخش Pipeline نمي باشد خصوصا اينكه جزييات ارائه شده در اين دو مدرك با يكديگر همخواني ندارند و موجب بروز مشكل در اجرا خواهد شد. لذا لازم است در مدرك مربوط به بخش Pipeline فقط جزييات مربوط به Line marker آورده شود و جزييات مربوط به سيستم حفاظت كانديك از اين مدرك حذف گردد. |  | BK-SUR-ENG-PPL-00-02291 | 14-Dec.-2021 | اصلاح شد
2 | اين مدرك قبلا با ترسميتال 101 با شماره مدرك BK-GNRAL-PEDCO-000-EL-DW-0005_D01 ارسال شده و كامنت بخش برق قبلاً ارسال گرديده است. اين رويه به هيچ وجه قابل قبول نمي باشد و در صورت تكرار مدرك بازگردانده خواهد شد. |  | BK-SUR-ENG-PPL-00-02291 | 14-Dec.-2021 | اصلاح شد
3 | لازم است در بخش Pipeline مدرك با همان عنوان قبلي Pipeline Standard Drawing for Line Marker كه فقط شامل نقشه و جزئيات Line Marker خط لوله مي باشد ارائه گردد. اطلاعات و جزئيات مربوط به حفاظت كاتديك در بخش برق ارائه شود. |  | BK-SUR-ENG-PPL-00-02291 | 14-Dec.-2021 | اصلاح شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Me.Karimi/F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:14-Dec-2021 |  |  |  |  | Date:14-Dec-2021