## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-RT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0700 |  |  | Transmital Date:3/8/2022
Document Title:Process Simulation Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0700 |  |  | Transmital Date:3/8/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0003 _D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مدرک "PFD" و "PROCESS SIMULATION REPORT" مقتضی است با توجه به نزدیک شدن دمای Discharge کمپرسور مرحله دوم (C-2102) در فصل زمستان به محدوده دمایی 150 درجه سانتیگراد ، فشار خروجی کمپرسور مرحله اول (C-2101) مطابق با مطالعات مقدماتی برابر با 21 Barg در نظر گرفته شود. |  | 1401-2294-33692 | 1401/02/01 | با توجه به استاندارد API 618-2008 (Section 6.5.1) دمای خروجی سیال نمی بایست از 150 درجه سانتیگراد بیشتر شود لذا شبیه سازی به گونه ای صورت پذیرفته شده که دمای سیال خروجی از کمپرسور کمتر از مقدار ذکر شده می باشد. نتیجه اشاره شده با راندمان 85 درصد توسط نرم افزار hysys محاسبه شده است. لازم به ذکر است باتوجه به پیشنهادات فنی دریافت شده از سازندگان میزان دمای خروجی کمپرسور مرحله دوم در حدود 145 درجه سانتیگراد ( با توجه به اینک شرکت های سازنده راندمان بالای 92 درصد را در محاسبات کمپرسور در نظر گرفته است ) محاسبه شده است. لازم به ذکر است به منظور تسریع روند پروژه و ثبت کامنت آن کارفرمای محترم مدرک فوق بدون هیچگونه تغییری به حضور ایفاد می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: