## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-IN-SP-0006_D02 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0495 |  |  | Transmital Date: 23/JAN/2022
Document Title: SPECIFICATION FOR ON/OFF /SHUTDOWN VALVES (ESD/MOV) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0006-PR-TR-0495 |  |  | Transmital Date:23/JAN/2022
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درخصوص مورد 5، متن خواسته شده این امور در مدرک درج گردد(نیازی به درج داده های فرآیندی نیست و منظور، ذکر مدارک مرجع فرآیندی است). |  | 1400-2294-441071 | 1400/12/17 | مطابق خواست کارفرمای محترم اعمال شد.
2 | در قسمت Scope هرگونه تغییرات یا اختلاف در مشخصات در هر مقطع از پروژه باید به تایید Client برسد. |  | 1400-2294-441071 | 1400/12/17 | تغییرات در نسخه های قبلی برای بررسی و تایید کارفرمای محترم همراه با Revision Mark و به رنگ خاکستری مشخص گردید و در این نسخه تغییری در مدرک ایجاد نشده است.
3 | با توجه به مفاد ماده 13 شرایط عمومی پیمان و نظر به وظایف و مسئولیت های کامل مالی/ قراردادی پیمانکار EPC/EPD ، در این مقطع با انجام تغییرات فوق الذکر جهت مدارک اشاره شده نظر دیگری مطرح نمی باشد. پیشبرد گام بعدی مهندسی مدارک و انتشار نسخه AFC بلامانع است. |  | 1400-2294-441071 | 1400/12/17 | مطابق خواست کارفرمای محترم اعمال شد. |  |  |  | 8
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: