## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-CN-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0672 |  |  | Transmital Date: 05/MAR/2022
Document Title: Calculation Note For Pipeline Wall Thickness |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-0672 |  |  | Transmital Date: 05/MAR/2022
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PL-CN-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در فایل محاسباتی ارسال شده موارد استخراج شده از استاندارد (تنش تسلیم، ضریب طراحی،...) درج گردد. |  | 01/2294/6202 | 1401/01/10 | - موارد مورد نظر درج شده اند.
2 | در محاسبه ضخامت لوله کشی می بایست Mill Tolerance نیز در نظر گرفته شود. در حالیکه در محاسبات لحاظ نشده است. |  | 01/2294/6202 | 1401/01/10 | - برای خط لوله در استاندارد ASME B31.8، پارامتر Mill Tolerance ذکر نشده است.
3 | مشخص گردد کد طراحی استاندارد ASME B31.3 مندرج در مدرک، شامل چه خطوطی است. |  | 01/2294/6202 | 1401/01/10 | - جریان های موجود در این مدرک با استانداردهای خط لوله طراحی شده اند.
4 | در بخش مراجع کلیه استانداردهای مربوطه IPS درج گردد. |  | 01/2294/6202 | 1401/01/10 | - اعمال گردید.
5 | میزان خوردگی مجاز C.A. پس از نهایی شدن مطالعات خوردگی تعیین می شود. |  | 01/2294/6202 | 1401/01/10 | - آخرین ویرایش مطالعات خوردگی در تعیین C.A لحاظ شده است.
6 | موارد اصلاح شده ردیف های اول تا سوم نامه پیشین مورد تایید است. |  | 4 / م ج/ 01 | 1401/01/09 | -
7 | مقدار C.A می بایست پس از نهایی شدن مدرک مطالعات خوردگی در نظر گرفته شود. |  | 4 / م ج/ 01 | 1401/01/09 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 13/03/2022 |  |  |  |  | Date: 13/03/2022