## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-DT-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1109 |  |  | Transmital Date: 6/22/2022
Document Title:Process Data Sheets For 2nd Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1109 |  |  | Transmital Date: 6/22/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظرات این امور بر روی مدرک PFD در نامه 336925 مورخ 01/02/01 می بایست در این مدرک لحاظ گردد. |  | 1401-2294-156959 | 1401/05/06 | با توجه به مفاد نامه آن کارفرمای محترم به شماره 336925 مورخ 01/02/01 و پاسخ این پیمانکار در خصوص موارد اشاره شده در نامه صدرالذکر تغییری بر روی مدرک فوق نخواهیم داشت
2 | برای جریان جرمی ورودی به کولر مابق اسناد پیمان ده درصد Over Design در نظر گرفته شود. |  | 1401-2294-156959 | 1401/05/06 | با توجه به Note 7 مدرک فوق به منظور طراحی تجهیز فوق ضریب Over Design ده درصد برای Duty و یا ماکزیمم دبی جرمی در نظر گرفته خواهد شد به نحوی که هر گزینه ای که بیشترین توان را مورد نیاز داشته باشد، به عنوان گزینه نهایی جهت طراحی و ساخت در نظر گرفته می شود. لازم به ذکر است مدرک فوق با Revision جدید D03 به حضور ایفاد می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021