## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-IN-SP-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0868 |  |  | Transmital Date: 4/27/2022
Document Title:Specification For ESD System |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-0868 |  |  | Transmital Date:4/27/2022
[5 empty] | CRS No:NISOC-BK-GNRAL-PEDCO-000-IN-SP-0003_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مورد 5، قسمت Scope جهت بسته خطوط لوله 4"و8" مورد بازنگری قرار گیرد. |  | 1401-2294-66361 | 1401/02/28 | مطابق توافقات اصلاح شد.
2 | در خصوص مورد2و3و6و8و9 نظر خاصی مطرح نمی باشد.. |  | 1401-2294-66361 | 1401/02/28 | -
3 | در خصوص موارد4و5و7: قسمت 6.2، جهت کلاستر بینک، نرم افزارهای سیستم ESD و سیستم DCSمستقل از هم در نظر گرفته شود |  | 1401-2294-66361 | 1401/02/28 | مطابق آخرین توافقات اصلاح شد.
4 | قسمت 6.2، جهت سیستم ESD بسته خطوط لوله 4"و8" توضیحات کافی داده شود. |  | 1401-2294-66361 | 1401/02/28 | مطابق آخرین توافقات اصلاح شد.
5 | قسمت 6.2، تعداد و آرایش ایستگاه کاری / مهندسی(E/OWS) متناسب با مدرک زیر برای هر بسته مورد بازنگری قرار گیرد. |  | 1401-2294-66361 | 1401/02/28 | مطابق آخرین توافقات اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Jan 2022 |  |  |  |  | Date: