## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-220-EL-DW-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0428 |  |  | Transmital Date: 04-Jan-2022
Document Title: Cable Route for Camp Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-EL-TR-0428 |  |  | Transmital Date: 04-Jan-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-220-EL-DW-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | The location of distribution transformer shall be specified in layout and the route between distribution transformer and MNDP shall be shown. |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | ترانس توزیع در کنار دیزل ژنراتور قرار می گیرد که در نقشه محل شروع برق رسانی مشخص می گردد. ولی با توجه به اینکه ساختمان سوئیچگیر و سایبان دیزل ژنراتور نهایی نشده است، این موضوع در ویرایش های بعدی به همراه ترنچ های داخل پست تکمیل می گردد.
2 | The cable size will be checked after submitting load list. |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | براساس محاسبات کابل در مدارک سر چاهی، سایز کابل های مورد نیاز صورت پذیرفت. لازم به ذکر است مدرک لیست بار با ترنسمیتال شماره 970 تولید شده است.
3 | MTO for cables shall be specified in a separated sheet and Length/type for each cable shall be specified. |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | علیرغم عدم وجود MTO در MDL پروژه فایل اکسل MTO تهیه و همراه مدارک ارسال می گردد.
4 | Street lighting feders (EDP-CMP-F01,02,04,05) shall be added in section layout 14. |  | BK-SUR-ENG-ELE-00-02677 | 2022-01-15 | مدرک بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 15-Jan-22 |  |  |  |  | Date: