## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0702 |  |  | Transmital Date: 3/9/2022
Document Title: Duty Specification for Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0702 |  |  | Transmital Date: 3/9/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اعداد عنوان شده در خصوص ميزان نقطه شبنم و نيز ميزان روغن با مدرك Basis of Design مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | این مقادیر بر اساس نیازمندی های پروژه و نیز درخواست سازنده تعیین شده اند.
2 | نقطه نظرات مندرج براي مدرك consumption در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | اعمال گردید.
3 | نهايي سازي ميزان و مشخصات مورد نياز نيتروژن، پس از دريافت اطلاعات سازنده امكان پذير خواهد بود. |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | مورد تایید است.
4 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-03818 | 2022-04-09 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: