## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0205 |  |  | Transmital Date:2021/1/02
Document Title:Process Flow Diagram - W018S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0205 |  |  | Transmital Date:2021/1/02
[5 empty] | CRS No:NISOC-CRS-BK-W018S-PEDCO-110-PR-PF-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه BK-PEDCO-NISOC-0008-PR-LT-16215 مورخ 00/08/12 به شماره وصول 21317 در خصوص مدرک منضم به ترنسمیتال صدرالذکر مقر گردد نقطه نظرات مربوط به نامه 288935 مورخ 00/09/02 در خصوص مدارک مزبور اعمال و ویرایش جدید با درج تغییرات مربوط به میزان آب همراه چاه ها در اسرع وقت ارسال گردد |  | 1401-2294-87488 | 1401/03/12 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: