## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:Process Flow Diagram - W007S |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0205 |  |  | Transmital Date:02/11/2021
Document Title:BK-W007S-PEDCO-110-PR-PF-0002 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0205 |  |  | Transmital Date:02/11/2021
[5 empty] | CRS No:PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نسخه PDF ارسالي فاقد صفحه دوم و جدول موازنه مواد مي باشد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
2 | شماره مدرك S&L نياز به بازنگري دارد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
3 | ضروريست نوت هاي نوشته در تمامي مدارك درخصوص مرجع ارائه شرايط فرايندي حذف و در مدرك Process Basis Of Design لحاظ گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
4 | مدرك Process Basis Of Design به عنوان مرجع مشخص گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
5 | وجود كاهنده سايز خط، شير دستي و غيره در PFD متداول نبوده و لازم است IPS مبناي طراحي قرار گيرد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
6 | ضروريست فشار بعد از چوك براساس ويرايش بروز شده هيدروليك خطوط لوله جرياني و نقطخ نظرات ارائه شده بر آن اصلاح گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
7 | تگ تله سنگ در دياگرام درج گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
8 | فشار قبل از چوك براساس پيوست 18 پيمان اصلاح گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | فشار قبل از چوک بر اساس نامه شماره 00/2290/223853 اعمال شده است .
9 | ضروريست نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-00-02020 | 2021-11-16 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: | Signature
| Date: 16/11/2021 |  |  |  |  | Date: