## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-PR-RT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0878 |  |  | Transmital Date: 4/30/2022
Document Title: Flow line Hydraulic Calculation Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-0878 |  |  | Transmital Date: 4/30/2022
[5 empty] | CRS No: NISOC-CRS-BK-W008N-PEDCO-110-PR-RT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0102-PR-LT-2726 مورخ 01/02/10 به شماره وصول 2864 د خصوص مدرک منضم به ترنسمیتال صدرالذکر نظرات این امور به شرح ذیل می باشد . با توجه به تغییر میزان برش آب مخازن آسماری و بنگستان میدان بینک مطابق نامه شماره 1401/2294/8112 مورخ 1401/01/15 مقتضی است کلیه مدارک مرتبط بازنگری و تصحیحات لازم صورت پذیرد . |  | 1401-2294-87489 | 1401/03/12 | اعمال گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: