## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W046S-PEDCO-110-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0729 |  |  | Transmital Date: 3/13/2022
Document Title:Process Flow Diagram - W0046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0729 |  |  | Transmital Date: 3/13/2022
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-PR-PF-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقتضی است با توجه به تغییر میزان برش آب مخازن آسماری و بنگستان میدان بینک مطابق نامه شماره 1401/2294/8112 مورخ 1401/01/15 مدرک ارسالی بازنگری و تصحیحات لازم صورت پذیرد. |  | 1401-2294-43234 | 1401/02/09 | اعمال گردید .
2 | بر روی خط لوله گودال سوخت به جای choke flange یک عدد شیر دروازه ای نصب گردد. |  | 1401-2294-43234 | 1401/02/09
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: