## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-TB-0002-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1031 |  |  | Transmittal Date: 6/6/2022
Document Title: TBE FOR Gas Dehydration Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-1031 |  |  | Transmital Date:6/6/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-TB-0002-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments
1 | TECHNICAL REQUIREMENTS value for A.09 (Fuel gas pressure) should be revised based on project documents. |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
2 | Turn down ratio of Regeneration equipment (A.16) for TJ proposal is not acceptable. |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
3 | Gas outlet water content that offer from Vendors/supplier should be meet project specification clearly. (A.17 ) |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
4 | “Bidder to specify” for Fuel Gas composition, Fuel gas specification, Capacity of package is not acceptable and should be specified by contractor and verified by Vendors/supplier |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
5 | Delham and MFS should be clarify how there is no pressure drop base on A.19 |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
6 | there aren’t enough process data in Delham proposal that referred to after P.O is not acceptable |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
7 | Contractor should be specify max. back pressure of Flare network for Approval of Vendors/supplier |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
8 | vendor should be recommended for capacity (percentage) of spill back line. |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | The required supplementary data will be provided after relevant PO, subject to Client's written approval.
9 | all Vendors/supplier should be confirm of process guarantee such as outlet dew point in min to max flowrate , required turn down, Utility consumption,….. |  | BK-SUR-ENG-MEC-01-04910 | 2022-06-28 | Required guarantees will be provided by selected Vendor.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 6/28/2022 |  |  |  |  | Date: