## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-DT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1111 |  |  | Transmital Date: 22/June/2022
Document Title: Data Sheets For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-ME-TR-1111 |  |  | Transmital Date: 22/June/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-ME-DT-0001-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the attached comment. |  | BK-SUR-ENG-MEC-01-05342 | 2022-08-03 | Please refer to attached file for Hirgan reply
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H. Ghadyani | Signature | M. Fakharian
| Date: 8/3/2022 |  |  |  |  | Date: 08/14/2022