## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-ME-DT-0002_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1100 |  |  | Transmital Date: 21/Jun/2022
Document Title: DATA SHEETS FOR POTABLE WATER TANK OF WELL PADS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-ME-TR-1100 |  |  | Transmital Date: 21/Jun/2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-ME-DT-0002_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محاسبات ارایه شده در خصوص میزان مصرف مورد تایید نبوده و لذا حجم مخزن نیز می بایست مورد بازنگری قرار گیرد. |  | 01/2294/165013 | 1401/05/11 | حجم مخزن بر اساس محاسبات سایزینگ مورد تایید کارفرمای محترم (سرپرست فرآیند) انجام شده و نهایی شده است.
2 | در مدارک ارسالی برخی جزییات ضروری سازه مخزن نشان داده نشده است. به عنوان نمونه نوع نردبان و نحوه اتصال آن به مخزن مشخص نیست. همچنین جهت نردبان مذکور محافظ در نظر گرفته نشده است. |  | 01/2294/165013 | 1401/05/11 | طرح نشان داده شده درحد شماتیک داده برگ است و قطعا در مراحل بعدی کار، مدارک سازنده با جزئیات دقیق تر ارائه خواهد گردید
3 | مجددا تاکید می گردد با توجه به مرتفع بودن مخزن، تمهیدات لازم جهت آبگیری مخزن می بایست در نظر گرفته شود. |  | 01/2294/165013 | 1401/05/11 | این نقطه نظر ارتباطی به داده برگ مخزن ندارد (ولی جهت استحضار، پر کردن مخزن توسط پمپ پرتابل همراه تانکر آب شرکت نفت صورت می پذیرد.)
4 | سایه بان اشاره شده در پاسخ داده برگ فنی در شماتیک ارسالی نشان داده شود. |  | 01/2294/165013 | 1401/05/11 | نظر کارفرمای محترم اعمال گردید.
5 | با توجه به تجارب پروژه های پیشین پیشنهاد این امور در نظر گرفتن مخزن فلزی است. |  | 01/2294/165013 | 1401/05/11 | با توجه به مشکلات گرم شدن آب و نیز پوشش دهی و زنگ زدگی مخازن فلزی و نیز عدم الزام قراردادی، پیشنهاد این پیمانکار استفاده از مخزن 5 لایه ی HDPE می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 08/14/2022