## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0703 |  |  | Transmital Date:3/9/2022
Document Title: Duty Specification for Chemical Injection Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0703 |  |  | Transmital Date: 3/9/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیشنهاد سازنده در خصوص میزان مصرف و جزییات محاسبه ارایه گردد. |  | 1401-2294-43236 | 1401/02/09 | طابق نوت شماره 1 مدرک chemical consumption میزان1 Pint/MMSCF ماده خوردگی بر اساس اطلاعات دریافتی از کارفرمای محترم و همچنین تجارب این پیمانکار در نظر گرفته شده است.
2 | تزریق ماده بازدارنده خوردگی به صورت دو مجموعه کم فشار و پر فشار(تغییر در مدارک پیمان) در دست بررسی است و نتیجه متعاقبا اعلام می گردد. |  | 1401-2294-43236 | 1401/02/09 | مورد تاییید قرار گرفته و تغییرات لازم اعمال گردیده است.
3 | مشخصا به P&ID اشاره و لیست جزییات هر پکیج در مدرک ارایه گردد. |  | 1401-2294-43236 | 1401/02/09 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: