## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0703 |  |  | Transmital Date: 3/9/2022
Document Title: Duty Specification for Chemical Injection Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0703 |  |  | Transmital Date:3/9/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در قسمت هاي مختلف مدرك ظرفيت تانك ماده بازدارنده خوردگي 4 روز و 7 روز قيد شده است ! |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اصلاح گردید.
2 | صرفا P&ID هاي مرتبط به عنوان مرجع معرفي گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اعمال گردید.
3 | فشار عملياتي مخزن متانول قيد گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | پیرو نتایج جلسات مهندسی ارزش و Hazop-Hazid مقرر گردید از پکیج متانول سایت موجود بینک به منظور تزریق متانول استفاده گردد لذا این مخزن از شرح خدمات پروژه خارج گردیده است.
4 | اطلاعات درج شده در خصوص مخزن متانول نادرست است. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | پیرو نتایج جلسات مهندسی ارزش و Hazop-Hazid مقرر گردید از پکیج متانول سایت موجود بینک به منظور تزریق متانول استفاده گردد لذا این مخزن از شرح خدمات پروژه خارج گردیده است.
5 | نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: