## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-SA-LI-0001_D01 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-0663 |  |  | Transmital Date:02/MAR/2022
Document Title: Hazard Source List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-TR-0663 |  |  | Transmital Date:02/MAR/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-SA-LI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است در خصوص تجهیز ردیف 9 ،شکل استاندارد مورد بازنگری قرار گردد. |  | 1401-2294-10280 | 1401/01/16 | ردیف 9 مورد بازنگری قرار گرفت.
2
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: