## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DC-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1028 |  |  | Transmital Date: 31 May 2022
Document Title: FIRE & GAS DETECTION DESIGN CRITERIA |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1028 |  |  | Transmital Date: 31 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DC-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس Note -2 مدرك مهندسي پايه Control System Overall Block Diagram، ادوات F&G و اتصال آن به سيستم موجود جز شرح كار پيمانكار مي باشد. لازم است پيمانكار بر اساس شرح كار تمام موارد مورد نياز را بررسي و اجرا نمايد. لازم به ذكر است شرح كار جديد جهت بهبود عملكرد و ايمني بيشتر سايت مي باشد لذا در صورت ارائه توضيحات بيشتر و تاييد ذينفع اصلي موضوع قابل بررسي بيشتر مي باشد. |  | BK-SUR-ENG-INS-01-04740 | 2022-06-18 | مطابق آخرین توافقات به دلایل زیر سیستم F&G در شرح کار این پیمانکار نمی باشد: 1-درمتن شرح کار تعریفی از ادوات F&G نشده است و تنها در یکی از مدارک شکل سیگنال F&G نشان داده شده است. 2- درجلسات HAZOP فرض عدم وجود F&G در منطقه سیاهمکان به توافق طرفین رسیده است. 3-در MDL کلیه مدارک F&G با همین دلایل حذف و به تایید کارفرما رسیده است. 4- مطابق بازدید انجام شده محوطهPIG RUNNING موجود نیز ادوات F&G وجود ندارد. 4- این مدرک به تایید کارفرما رسیده است. انتظار می رود پس از تایید NISOC شرکت محترم پترو ایران نیز اصراری به اضافه شدن شرح کار بدون ادله کافی نداشته باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 Jun 2022 |  |  |  |  | Date: